COMPLETE CLIENT JOURNEY From First Contact to Ongoing Fulfillment Powered by GoHighLevel (GHL) · Google Ads · Meta Ads · Social Media Marketing Agency for Contractors ¦ San Diego, CA ¦ Internal Operations Master Guide

📌 HOW TO USE THIS DOCUMENT This is the master operations guide for our entire client lifecycle — from the moment a lead enters our pipeline to ongoing monthly fulfillment across all services. Every GoHighLevel (GHL) action is called out in an orange box so team members know exactly what to do in the platform at each step. Services covered: Google Ads, Meta Ads, Local Service Ads (LSA), Social Media & Content, and CRM/pipeline management. This guide is used by: Sales Reps, Account Managers, Ad Specialists, Content Specialists, and Onboarding Coordinators.

THE COMPLETE CLIENT PIPELINE — AT A GLANCE

| LEAD IN → | SALES CALL → | PROPOSAL → | CONTRACT → | ONBOARDING → | BUILD → | LAUNCH → | FULFILLMENT |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Day 0 → | Day 1–3 → | Day 3–5 → | Day 5–7 → | Day 7–10 → | Day 10–18 → | Day 18–22 → | Day 22+ |
| --- | --- | --- | --- | --- | --- | --- | --- |

| Phase | Timeframe | What Happens |
| --- | --- | --- |
| LEAD IN | Day 0 | Lead enters GHL pipeline from ad, referral, or outbound. Assigned to Sales Rep. Automated welcome sequence triggers. |
| SALES CALL | Day 1–3 | Discovery call booked via GHL calendar. Sales rep qualifies, presents value, handles objections. |
| PROPOSAL | Day 3–5 | Proposal sent via GHL. Automated follow-up sequence runs until opened and signed. |
| CONTRACT | Day 5–7 | Contract signed via GHL (DocuSign integration). Payment collected. Opportunity moved to Won. |
| ONBOARDING | Day 7–10 | Welcome email + Intake Form sent. Kickoff call scheduled. GHL sub-account created for client. |
| BUILD | Day 10–18 | Campaign build, tracking setup, content planning. GHL automations configured for lead routing. |
| LAUNCH | Day 18–22 | Internal QA. Client review call. All campaigns go live. GHL lead notifications active. |
| FULFILLMENT | Day 22+ | Ongoing: weekly optimization, monthly content shoot, monthly reporting, GHL pipeline updates. |

| 1 | LEAD CAPTURE & PIPELINE ENTRY Day 0 — The moment a prospect enters our world |
| --- | --- |

🎯  HOW LEADS ENTER OUR PIPELINE

Every lead — regardless of source — must be entered into GoHighLevel immediately. No leads tracked in spreadsheets, sticky notes, or personal phones. GHL is the single source of truth.

| INBOUND LEAD SOURCES • Our own Google Ads (lead form or call) • Our own Meta/Facebook Ads (lead form) • Our website contact form • Organic Google search + GBP call • Referral from existing client • Referral from partner (roofer → HVAC, etc.) • Instagram/Facebook DM or comment • Thumbtack / Bark / Angi lead (forwarded in) | OUTBOUND LEAD SOURCES • Cold call by Sales Rep • LinkedIn outreach • Door-to-door / in-person at job sites • Networking events (NARI, BNI, Chamber) • Cold email sequence via GHL • Follow-up on old dead leads (GHL re-engagement) • Direct mail respondents • Trade show / expo contacts |
| --- | --- |

🔶 GO HIGH LEVEL: CREATE CONTACT → Contacts → + New Contact — Fill: Name, Phone, Email, Business Name, Lead Source, Service Interest, City/Zip

⚙️  GHL AUTOMATION — LEAD ENTRY TRIGGERS

The following automations fire the moment a new contact is created or enters the pipeline. These run without any manual action from the team.

AUTOMATED ACTIONS ON NEW LEAD ENTRY (GHL Workflow) Trigger: New Contact Created → Tag: 'New Lead' Action 1 (Immediate): Send automated SMS to lead Text: 'Hey [First Name]! This is [Agency Name] — we got your info and want to learn more about your contracting business. What's the best time to connect this week?' Action 2 (5 min delay): Send automated Email Subject: 'Quick question about your marketing, [First Name]' Body: Short intro + link to book a call on GHL calendar Action 3 (Immediate): Create Opportunity in Pipeline → Stage: 'New Lead' Assign to: Available Sales Rep (round-robin if multiple reps) Action 4 (Immediate): Notify assigned Sales Rep via SMS + GHL app notification Message: 'New lead: [Name] — [Business] — [Service Interest]. Follow up within 5 min.' Action 5 (1 hour, if no response from lead): Follow-up SMS #2 'Just checking in — happy to answer any questions about what we do for SD contractors.'

🔶 GO HIGH LEVEL: PIPELINE → Opportunities → Confirm new card in 'New Lead' stage → Assign Sales Rep → Add notes from lead source

LEAD SPEED-TO-CONTACT RULE — NON-NEGOTIABLE Studies show that responding to a lead within 5 minutes vs. 30 minutes increases conversion by over 300%. Our standard: Sales Rep must make first personal contact (call or personalized SMS) within 15 minutes of a new lead during business hours. After hours: GHL automation handles the first touch. Sales Rep follows up first thing next morning — no exceptions. If a lead is not contacted within 15 minutes during business hours, it must be escalated to the Sales Manager.

| 2 | SALES PROCESS — DISCOVERY TO CLOSE Days 1–7 — Converting a prospect into a paying client |
| --- | --- |

📞  PHASE 2A — DISCOVERY CALL

The Discovery Call is a 30–45 minute conversation to understand the contractor's business, qualify them, and identify which of our services fits best. It is not a pitch — it is a diagnosis.

🔶 GO HIGH LEVEL: CALENDAR → Book call via GHL Calendar link (send to prospect) OR manually create appointment → Move Opportunity to 'Call Scheduled'

DISCOVERY CALL FRAMEWORK (30–45 MIN) OPEN (5 min): Build rapport. Ask about their business, how long they've been in San Diego, what they specialize in. DIAGNOSE (15 min): Ask the pain questions — 'Where does most of your work come from right now?' 'What happens when you hit a slow month?' 'Have you tried any marketing before? What happened?' 'What does an average job bring you in revenue?' 'If you could wave a wand — what does your business look like in 12 months?' PRESENT (10 min): Based on what they told you, present the specific services that solve their specific pain. Not a menu — a prescription. HANDLE OBJECTIONS (5 min): Use objection handling guide. Never argue — acknowledge and redirect. CLOSE / NEXT STEP (5 min): Either close on the call, or set a specific next-step with a date and time. Never end a call without a next step.

🔶 GO HIGH LEVEL: PIPELINE → Move Opportunity to 'Discovery Call Complete' → Add call notes in GHL contact record → Update opportunity value field

📄  PHASE 2B — PROPOSAL

Proposals go out within 24 hours of the discovery call — while the conversation is fresh. Proposals that sit longer than 48 hours see dramatically lower close rates.

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Build proposal using GHL Proposal/Estimate tool — include services, deliverables, pricing, and timeline | Sales Rep | Within 24 hrs of call | ☐ |
| Customize the proposal with the prospect's business name, service area, and specific pain points discussed on the call | Sales Rep | Within 24 hrs of call | ☐ |
| Send proposal via GHL — do NOT email a PDF manually (GHL tracks opens) | Sales Rep | Within 24 hrs of call | ☐ |
| Move Opportunity to 'Proposal Sent' in pipeline | Sales Rep | Day of send | ☐ |
| GHL automation triggers: proposal open notification sent to Sales Rep (act on it immediately) | GHL Auto | Auto | ☐ |
| If proposal not opened within 24 hrs: send follow-up SMS/call from Sales Rep | Sales Rep | 24 hrs after send | ☐ |
| If proposal opened but not signed within 48 hrs: GHL automation sends soft nudge email | GHL Auto | 48 hrs | ☐ |
| If not signed after 72 hrs: Sales Rep calls to address questions or objections directly | Sales Rep | 72 hrs | ☐ |

🔶 GO HIGH LEVEL: PROPOSALS → Create Proposal → Select Template → Customize → Send via GHL link → Monitor open notifications in real time

PROPOSAL CONTENT — WHAT TO INCLUDE 1. Cover page: Client business name, logo (if available), date, and 'Prepared by [Agency Name]' 2. The Problem: Restate what they told you — show you listened 3. Our Solution: Specific services recommended and why each one fits their situation 4. Deliverables: Exactly what they get (campaigns, posts per month, reports, calls, etc.) 5. Timeline: When they can expect results and key milestones 6. Investment: Clear pricing — management fee + ad spend (separate line items) 7. Social Proof: 1–2 local contractor case studies relevant to their trade 8. Next Steps: Specific CTA — 'Sign below and we'll schedule your kickoff call' 9. FAQ: Address top 3 objections proactively (cost, results timeline, contract length)

✍️  PHASE 2C — CONTRACT & PAYMENT

Once the proposal is accepted, the contract is signed and payment is collected through GHL. No work begins until both are complete.

🔶 GO HIGH LEVEL: CONTRACTS → Send Contract via GHL DocuSign integration → Set up Payment via GHL Payments (Stripe) → Move Opportunity to 'Contract Sent'

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Send contract via GHL's contract/signature tool (DocuSign integration) | Sales Rep | Same day as acceptance | ☐ |
| Contract includes: services, deliverables, payment terms, cancellation policy, ad spend authorization | Sales Rep | Pre-built template | ☐ |
| Collect first month payment via GHL Payments (Stripe) — management fee + first month ad budget | Sales Rep | On signature | ☐ |
| Set up recurring payment in GHL/Stripe for subsequent months | Sales Rep | On signature | ☐ |
| Move Opportunity to 'WON' in GHL pipeline — trigger the Won automation | Sales Rep | Immediately on payment | ☐ |
| Tag contact: 'Active Client' — remove tag: 'Lead' | GHL Auto | Auto on Won | ☐ |
| Notify Onboarding Coordinator via GHL internal notification — handoff begins | GHL Auto | Auto on Won | ☐ |
| Send client a 'Welcome to the family' SMS from Sales Rep — personal touch | Sales Rep | Within 1 hr of signing | ☐ |

🔶 GO HIGH LEVEL: OPPORTUNITY → Mark as WON → GHL triggers Welcome Sequence → Onboarding Coordinator receives task notification → Client moved to 'Onboarding' pipeline stage

GHL WON AUTOMATION — FIRES AUTOMATICALLY ON CLOSE Trigger: Opportunity marked as WON Action 1: Send client automated Welcome Email Subject: 'Welcome to [Agency Name] — Here's what happens next' Body: Introduce the onboarding process, who their AM will be, and what to expect in the next 48 hours. Action 2: Create Onboarding Task for Onboarding Coordinator in GHL Tasks Task: 'New Client Onboarding — [Client Name] — Services: [list]' Due: 24 hours from now Action 3: Add client to 'Active Clients' GHL list Action 4: Notify Account Manager via SMS and GHL app notification 'New client assigned: [Name] — [Business] — [Services]. Kickoff call needed within 48 hrs.' Action 5: Start 30-day onboarding progress tracker in GHL

| 3 | CLIENT ONBOARDING — GHL SETUP & KICKOFF Days 7–10 — Setting the foundation for the entire relationship |
| --- | --- |

🏗️  PHASE 3A — GHL SUB-ACCOUNT CREATION

Every client gets their own GoHighLevel sub-account. This is where all their leads, conversations, automations, reporting, and calendar live. Set it up completely before the kickoff call.

🔶 GO HIGH LEVEL: AGENCY VIEW → Sub-Accounts → + New Sub-Account → Fill all client details → Assign to Account Manager

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Create GHL sub-account — business name, address, phone, website, timezone (Pacific) | Onboarding Coordinator | Day 7 | ☐ |
| Set up GHL Phone Number for client (Twilio) — this is their lead tracking number | Onboarding Coordinator | Day 7 | ☐ |
| Configure GHL Conversation inbox — email, SMS, Facebook Messenger, Instagram DM | Onboarding Coordinator | Day 7 | ☐ |
| Connect client's Facebook Business page to GHL (for social messaging and ad lead forms) | Onboarding Coordinator | Day 7 | ☐ |
| Connect client's Google Business Profile to GHL (for review management) | Onboarding Coordinator | Day 7 | ☐ |
| Import client's existing contacts/leads into GHL (from spreadsheet or old CRM) | Onboarding Coordinator | Day 8 | ☐ |
| Build client's GHL pipeline — stages: New Lead, Contacted, Estimate Sent, Job Booked, Completed, Review Requested | Onboarding Coordinator | Day 8 | ☐ |
| Set up GHL Calendar for client — booking link, availability hours, appointment types (Free Estimate, Callback) | Onboarding Coordinator | Day 8 | ☐ |
| Install GHL tracking snippet on client's website (or send to their web developer) | Ad Specialist | Day 8 | ☐ |
| Activate GHL Reputation Management — connect to Google Reviews, set up auto-review request | Onboarding Coordinator | Day 9 | ☐ |
| Build core GHL automations (see Automation section below) | Onboarding Coordinator | Day 9 | ☐ |
| Test all automations end-to-end before kickoff call | Onboarding Coordinator | Day 10 | ☐ |

⚡  PHASE 3B — CORE GHL AUTOMATIONS TO BUILD FOR EVERY CLIENT

These 6 automations are the backbone of the client's lead management system. Build all of them before launch — they run 24/7 on the client's behalf.

AUTOMATION 1 — NEW LEAD INSTANT RESPONSE Trigger: New lead received (from any source — ad form, website, manual entry) Delay: Immediate (0 minutes) SMS: 'Hi [First Name]! Thanks for reaching out to [Business Name]. We'll call you shortly to schedule your free estimate. — [Owner Name]' Email: Branded welcome email with company info and what to expect Internal: Notify owner/office via SMS — 'New lead: [Name] [Phone]. Call within 5 min.' GHL Task: Create follow-up task assigned to owner — due in 30 minutes

AUTOMATION 2 — MISSED CALL TEXT-BACK Trigger: Incoming call to GHL number → Call NOT answered Delay: Immediate SMS: 'Hey, we just missed your call at [Business Name]! We'd love to help. Call us back at [number] or reply here and we'll get right back to you.' WHY THIS MATTERS: Contractors miss calls constantly when they're on the job. This automation captures leads that would otherwise go to a competitor.

AUTOMATION 3 — ESTIMATE FOLLOW-UP SEQUENCE Trigger: Opportunity moved to 'Estimate Sent' stage Day 1 (same day): Email confirming estimate was sent + what's included Day 2: SMS check-in — 'Did you get a chance to look at the estimate? Happy to answer any questions.' Day 4: Email follow-up — include a relevant review or before/after from similar job Day 7: Final SMS — 'Just checking in one last time — still interested in [service]? We can get started this week.' If no response after Day 7: Move to 'Unresponsive' stage. Tag: 'Re-engage in 30 days'

AUTOMATION 4 — JOB BOOKED CONFIRMATION & REMINDER Trigger: Opportunity moved to 'Job Booked' stage Immediate: Booking confirmation SMS — 'Your [service] is confirmed for [date/time]. Our team will be there! — [Business Name]' 24 hrs before: Reminder SMS — 'Reminder: [Business Name] is coming tomorrow at [time]. See you then!' 2 hrs before: Final reminder SMS — 'We're on our way! See you at [time]. Call [number] if you need anything.'

AUTOMATION 5 — POST-JOB REVIEW REQUEST Trigger: Opportunity moved to 'Completed' stage Delay: 2 hours after completion SMS: 'Thanks for choosing [Business Name], [First Name]! We hope everything looks great. If you have a minute, a quick Google review means the world to us: [Google Review Link]' Day 3 (if no review left): Email follow-up — 'How did we do?' with review link WHY: Automating review requests after every job is the fastest way to build a 5-star Google profile. Most contractors get 10x more reviews within 60 days.

AUTOMATION 6 — REACTIVATION CAMPAIGN (DORMANT LEADS) Trigger: Contact tag 'Re-engage in 30 days' + 30 days have passed SMS 1: 'Hey [First Name], it's [Business Name]. We noticed we connected a while back about [service]. Are you still looking? We have some availability coming up in your area.' Day 3: Email — 'What's changed? We're still here when you're ready.' Include a recent project photo. Day 7: Final SMS — 'Last check-in — still interested in [service]? No worries if not, just let us know.' If no response: Archive contact. Tag: 'Archived — 6-month re-touch'

📞  PHASE 3C — KICKOFF CALL

The kickoff call happens on Day 10 — after GHL is fully set up. The AM walks the client through their new system AND gathers everything needed for campaign build.

🔶 GO HIGH LEVEL: CALENDAR → Schedule Kickoff Call → Use GHL appointment type: 'Client Kickoff' → Send calendar invite with Zoom link → Remind via GHL automation 24 hrs before

KICKOFF CALL AGENDA — 60 MINUTES 0:00–0:10 Welcome & relationship building. Introduce the full team they'll be working with. 0:10–0:20 GHL Walkthrough — show client their sub-account: → Conversations inbox (where all their leads will appear) → Pipeline view (how to track their jobs) → Calendar (how clients will book directly) → Missed call text-back demo — show it working live 0:20–0:35 Campaign intake — collect remaining information needed for ad/social build: → Service priorities, target zip codes, avg job value, offer/promotion → Competitors to research, differentiators, brand assets → Call handling process, hours, after-hours coverage 0:35–0:50 Strategy preview — show them the plan: which campaigns launch first and why. 0:50–0:60 Next steps — timeline to launch, who contacts them and when, first check-in date.

🔶 GO HIGH LEVEL: POST-KICKOFF → Log call notes in GHL Contact Record → Update Opportunity to 'Kickoff Complete' → Create Tasks for Ad Specialist and Content Specialist with deadlines

| 4 | CAMPAIGN BUILD — ALL SERVICES Days 10–18 — Building everything before launch |
| --- | --- |

🔧  TRACKING SETUP — ALWAYS FIRST

No campaign goes live without verified tracking. This protects the client's budget and our ability to prove results.

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Install Google Tag Manager on client website (or coordinate with their developer) | Ad Specialist | Day 10 | ☐ |
| Set up Google Analytics 4 — verify data flowing | Ad Specialist | Day 10 | ☐ |
| Create Google Ads conversion actions: phone call, form submit, quote request | Ad Specialist | Day 11 | ☐ |
| Set up CallRail tracking number — route to client's real number | Ad Specialist | Day 11 | ☐ |
| Install Meta Pixel on website — verify via Meta Pixel Helper | Ad Specialist | Day 11 | ☐ |
| Connect GHL form submissions to Google Ads and Meta as conversion events | Ad Specialist | Day 12 | ☐ |
| Verify ALL conversions firing in Google Tag Assistant — do not proceed until green | Ad Specialist | Day 12 | ☐ |
| Set up GHL → Zapier/API bridge to push form leads into client's GHL pipeline automatically | Onboarding Coordinator | Day 12 | ☐ |

🔶 GO HIGH LEVEL: SETTINGS → Integrations → Connect Google Ads account (for call reporting) → Connect Facebook (for lead form sync) → Test lead flow end-to-end: submit test lead → verify it appears in GHL Conversations and Pipeline

📢  GOOGLE ADS BUILD

- Create campaigns by service category — never mix services in one campaign

- Build ad groups: 2–4 per campaign, tightly themed keyword clusters

- Write Responsive Search Ads (RSAs): 15 headlines + 4 descriptions per ad group minimum

- Apply all required assets: call, location, sitelinks (4+), callouts (6+), structured snippets, images

- Set geographic targeting: San Diego zip codes — never national, never radius-only

- Set bidding: Manual CPC for first 30 days → Maximize Conversions at 15+ conversions

- Apply negative keyword list from master account-level list + service-specific negatives

- Link Google Ads to GA4, Search Console, and GHL phone number

🔶 GO HIGH LEVEL: REPORTING → Connect Google Ads to GHL Reporting Dashboard → Set up automated weekly performance snapshot sent to AM

📱  META ADS BUILD

- Campaign 1 — Prospecting: homeowners 30–65, San Diego DMA, home improvement interests

- Campaign 2 — Retargeting: website visitors (30 days), video viewers (50%+), page engagers

- Creative: minimum 3 static images + 1 video/Reel + 1 carousel per campaign at launch

- Lead forms: build Meta Instant Lead Form for quote requests — sync to GHL automatically

- All Meta leads auto-flow into GHL pipeline via Facebook lead sync integration

🔶 GO HIGH LEVEL: INTEGRATIONS → Facebook → Connect Meta Business Manager → Enable Lead Form Sync → Test: submit test lead on Meta form → Verify appears in GHL Conversations within 60 seconds

📍  GOOGLE LOCAL SERVICE ADS (LSA)

- Submit business verification documents — license, insurance, background check

- Build LSA profile: services, hours, service areas by zip code, photos, description

- Set weekly budget — typically $200–$600/week for San Diego contractors

- Enable both call leads and message leads

- Route LSA call notifications to GHL phone number for unified inbox

🔶 GO HIGH LEVEL: PHONE → Verify that LSA calls route through GHL number → Test inbound call → Confirm call recording active and logged in GHL contact record

📸  SOCIAL MEDIA & CONTENT SETUP

- Complete Strategy Session — define 5 content pillars, brand voice, platform priority

- Build content calendar template in Google Drive — shared with client

- Schedule first content shoot — confirm date, location, shot list

- Connect all social accounts to GHL social planner for scheduling

- Set up GHL Reputation Management for Google review monitoring and response

🔶 GO HIGH LEVEL: SOCIAL PLANNER → Connect Facebook, Instagram, Google Business Profile → Test post scheduling → Set up approval workflow if client wants to review before posting

| 5 | QA, CLIENT REVIEW & LAUNCH Days 18–22 — Nothing goes live without passing QA |
| --- | --- |

✅  INTERNAL QA CHECKLIST

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| All conversion tracking verified: call tracking, form submits, GHL lead entries all firing | Ad Specialist | Day 18 | ☐ |
| All campaigns have correct geo targeting — zip codes confirmed, NOT national | Ad Specialist | Day 18 | ☐ |
| Ad scheduling set — campaigns run during client's service hours (or 24/7 if they have coverage) | Ad Specialist | Day 18 | ☐ |
| All RSAs show 'Good' or 'Excellent' ad strength in Google Ads | Ad Specialist | Day 18 | ☐ |
| All ad extensions/assets active and approved | Ad Specialist | Day 18 | ☐ |
| GHL automations tested end-to-end: new lead → SMS fires → task created → pipeline updated | Onboarding Coordinator | Day 19 | ☐ |
| Missed call text-back tested — call GHL number, don't answer, verify SMS sends | Onboarding Coordinator | Day 19 | ☐ |
| Meta lead form tested — submit test lead, verify appears in GHL within 60 seconds | Ad Specialist | Day 19 | ☐ |
| LSA profile live and verified — showing 'Google Guaranteed' badge | Ad Specialist | Day 19 | ☐ |
| GHL reporting dashboard populated — AM can see all key metrics in one view | Onboarding Coordinator | Day 19 | ☐ |
| Review request automation tested — confirm SMS and email send correctly | Onboarding Coordinator | Day 20 | ☐ |
| Second team member spot-check complete — Senior AM signs off | Senior AM | Day 20 | ☐ |

👤  CLIENT REVIEW CALL — PRE-LAUNCH

A 30-minute screen share with the client before anything goes live. This is the last checkpoint and a major trust-building moment.

CLIENT REVIEW CALL AGENDA (30 MIN) 1. Screen share — walk through GHL dashboard: their conversations inbox, pipeline, calendar 2. Demo the missed-call text-back live — call their number, don't answer, show the text fires 3. Show the ad campaigns — read top headlines, confirm targeting area on map 4. Explain the lead flow: 'When someone clicks your Google ad → they call or fill a form → it appears here in GHL instantly → you get a text notification' 5. Walk through the automations they have: new lead response, estimate follow-up, review request 6. Set expectations on launch: learning phase, first 30 days data collection, when to expect leads 7. First content shoot date confirmation (if applicable) 8. Confirm go-live date and who notifies whom

🔶 GO HIGH LEVEL: PIPELINE → Move Opportunity to 'Pre-Launch Review Complete' → Set launch date in GHL → Create 'Launch Day' task for AM and Ad Specialist

🚀  LAUNCH DAY

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Set all Google Ads campaigns to 'Enabled' — monitor for first 2 hours for disapprovals | Ad Specialist | Launch day | ☐ |
| Set all Meta campaigns to 'Active' — monitor for policy flags | Ad Specialist | Launch day | ☐ |
| Confirm LSA is active and receiving impressions in dashboard | Ad Specialist | Launch day | ☐ |
| Send 'We're Live!' email to client via GHL — include screenshots of active campaigns | AM | Launch day | ☐ |
| Send personal SMS to client from AM: 'Your campaigns are live! Keep an eye on your GHL inbox — leads will start coming in.' | AM | Launch day | ☐ |
| Log launch date in GHL Contact Record notes — anchor for all future milestone dates | AM | Launch day | ☐ |
| Set GHL reminder task: Day 7 check-in call with client | AM | Launch day | ☐ |
| Set GHL reminder task: Day 30 First Month Review | AM | Launch day | ☐ |

🔶 GO HIGH LEVEL: PIPELINE → Move Opportunity/Contact to 'Active Client — Live' stage → Start 30-day launch tracker → All future activities tracked in GHL Contact Record

| 6 | ONGOING FULFILLMENT — WEEKLY & MONTHLY RHYTHM Day 22+ — This is where results compound |
| --- | --- |

📅  WEEKLY RHYTHM — EVERY WEEK WITHOUT EXCEPTION

| MONDAY — AD OPTIMIZATION ☐ Review search terms — add negatives, promote converters ☐ Pause keywords with 50+ clicks / 0 conversions ☐ Check impression share — target 60%+ ☐ Review Quality Scores — fix anything below 5/10 ☐ Check budget pacing — on track for month? ☐ Meta: check frequency — rotate creative if above 3.0 ☐ Log all changes in GHL client record notes WEDNESDAY — GHL PIPELINE REVIEW ☐ Review client's GHL pipeline — any stuck leads? ☐ Check automations firing correctly — no failed workflows ☐ Review conversation inbox — any unanswered leads? ☐ Check review requests sent/received this week ☐ Flag any issues to AM immediately | FRIDAY — AM CLIENT PULSE CHECK ☐ Review lead volume for the week — on pace? ☐ Check call recordings in GHL — 3–5 spot checks ☐ Any client messages/complaints unresolved? ☐ Review GBP posts scheduled for next week ☐ Note any wins to share with client proactively ☐ Prepare agenda for any scheduled check-in calls ONGOING — CONTENT SPECIALIST ☐ Community management: reply to all comments/DMs within 24 hrs ☐ Monitor all tagged mentions and shares ☐ Respond to all Google reviews via GHL ☐ Queue next week's posts if not already scheduled ☐ Flag any negative content to AM immediately |
| --- | --- |

🔶 GO HIGH LEVEL: REPORTS → Open Client Sub-Account → Check GHL Dashboard: Leads This Week, Conversations, Pipeline Movement, Missed Calls, Review Count → Note any anomalies in client record

📊  MONTHLY RHYTHM — FIRST WEEK OF EVERY MONTH

| Task / Action | Owner | Timeline | Done? |
| --- | --- | --- | --- |
| Pull Google Ads performance: impressions, clicks, conversions, CPL, spend — export to reporting template | Ad Specialist | Day 1–2 | ☐ |
| Pull Meta Ads performance: reach, leads, CPL, ROAS — export to reporting template | Ad Specialist | Day 1–2 | ☐ |
| Pull GHL reporting: total leads, calls, GBP views, review count, automation performance | AM | Day 1–2 | ☐ |
| Pull social media analytics: engagement, reach, follower growth, top posts | Content Specialist | Day 1–2 | ☐ |
| Identify top 3 wins and top 3 areas for improvement across all channels | AM | Day 2 | ☐ |
| Build monthly report — one page summary + supporting data (use GHL reporting + Looker Studio) | AM | Day 3–4 | ☐ |
| Record Loom video walkthrough of the report (5 min max — conversational, not formal) | AM | Day 4 | ☐ |
| Send report + Loom to client via email by the 5th of the month | AM | Day 5 | ☐ |
| Update client's Opportunity record in GHL — log MRR, services active, next renewal date | AM | Day 5 | ☐ |
| Schedule content shoot for the month (if on content plan) — confirm date with client | Content Specialist | Day 1–7 | ☐ |
| Prep next month's ad strategy adjustments based on data — document in GHL notes | Ad Specialist | Day 5–7 | ☐ |

🔶 GO HIGH LEVEL: REPORTING → GHL Dashboard → Export Monthly Report PDF → Combine with Loom link → Send via GHL Email or direct email with GHL logged conversation

🔄  QUARTERLY STRATEGY REVIEW

Every 90 days, the AM schedules a 45-minute Quarterly Review with the client. This is a strategic conversation, not just a data review. It also serves as the primary upsell checkpoint.

QUARTERLY REVIEW AGENDA (45 MIN) 0:00–0:10 90-day performance overview — what the data shows across all channels 0:10–0:20 What's working — double down conversation: which channels/content are winning? 0:20–0:30 What needs to change — honest assessment. What are we adjusting next quarter? 0:30–0:38 Competitive landscape — any new competitors appearing in their space? 0:38–0:45 Next quarter plan — present 2–3 strategic recommendations. Include upsell if appropriate. UPSELL CHECKPOINT: If client is not on all services, present the business case for adding: → Social Media if only on ads ¦ → LSA if only on Google Search ¦ → SEO retainer add-on → Increase ad budget if ROI data supports it ¦ → Website redesign if conversion rate is low

🔶 GO HIGH LEVEL: PIPELINE → Open client Opportunity → Review MRR, services, tenure → Update 'Next Quarterly Review' date → Log upsell conversation outcome → If upsell agreed: create new Opportunity for additional service

| 7 | GHL MASTER SETUP — AGENCY-LEVEL CONFIGURATION How our GoHighLevel agency account is structured |
| --- | --- |

🏢  AGENCY ACCOUNT STRUCTURE

Our GoHighLevel agency account is the master hub. Every client gets their own sub-account. Our internal operations, team communications, and agency-level automations live at the agency level.

| AGENCY-LEVEL (OUR ACCOUNT) • Team member accounts and permissions • Master pipeline templates (cloned to each client) • Master automation templates (cloned to each client) • Agency-level reporting (all clients view) • Billing and subscription management • Our own sales pipeline (for new client acquisition) • Agency snapshot library — deploy to new sub-accounts | PER-CLIENT SUB-ACCOUNT • Client's own contacts and conversations • Client's pipeline (New Lead → Booked → Complete) • Client's automations (lead response, reminders, reviews) • Client's calendar and booking system • Client's reputation management (Google reviews) • Client's social planner (post scheduling) • Client's reporting dashboard |
| --- | --- |

👥  TEAM ROLES & GHL ACCESS LEVELS

| Role | Primary Responsibilities | GHL Access Level |
| --- | --- | --- |
| Sales Rep | Manages prospects in agency sales pipeline, sends proposals and contracts via GHL, logs all calls/notes | Agency Level — Sales pipeline access only |
| Onboarding Coordinator | Creates sub-accounts, builds automations, tests lead flows, sets up pipelines for new clients | Agency Level — Sub-account creation + full access to new accounts |
| Account Manager | Manages all active client sub-accounts, monthly reporting, client communications, quarterly reviews | Agency Level — Full access to assigned client sub-accounts |
| Ad Specialist | Accesses client GHL for tracking integration, call number routing, lead sync verification | Sub-account level — Integrations + reporting tab only |
| Content Specialist | Uses GHL Social Planner for post scheduling, monitors GHL review management | Sub-account level — Social Planner + Reputation tab |
| Senior AM / Director | Full agency-level access, reviews all pipelines, manages team permissions, reviews reports | Full agency admin access |

📋  GHL PIPELINE — AGENCY SALES PIPELINE (FOR OUR OWN LEADS)

We use GHL to manage our own new client acquisition pipeline. Every prospect our sales team is working lives here.

| New Lead → | Contacted → | Call Booked → | Proposal → | Negotiating → | WON ✓ → | LOST ✗ |
| --- | --- | --- | --- | --- | --- | --- |

PIPELINE STAGE DEFINITIONS — AGENCY SALES PIPELINE New Lead: Contact just entered — not yet reached by phone/SMS Contacted: First personal contact made — call or personalized message sent Call Booked: Discovery call scheduled in GHL calendar Proposal Sent: Proposal sent via GHL — tracking open status Negotiating: Prospect engaged, discussing terms, pricing, or services WON: Contract signed + payment received → triggers onboarding automation LOST: Prospect went with competitor or opted out → tag with loss reason for analysis

| 8 | REPORTING, RETENTION & GROWTH Keeping clients happy, proving value, and growing MRR |
| --- | --- |

📈  THE MONTHLY REPORT — STRUCTURE & DELIVERY

The monthly report is our most important retention tool. It proves value, builds trust, and preempts cancellation conversations before they start.

MONTHLY REPORT MUST INCLUDE (ALL CLIENTS) SECTION 1 — EXECUTIVE SUMMARY (3 sentences max) 'This month we generated X leads at $Y cost per lead. Top performer was [channel]. Next month we will [specific action].' SECTION 2 — KEY METRICS (pull from GHL + ad platforms) Total Leads ¦ Calls ¦ Form Fills ¦ Cost Per Lead ¦ Total Spend ¦ GBP Views ¦ Reviews Received SECTION 3 — CHANNEL BREAKDOWN Google Search: impressions, clicks, CTR, conversions, CPL Google LSA: leads, cost per lead, disputes Meta Ads: reach, leads, CPL Social Media: followers, engagement rate, top post, GBP posts SECTION 4 — GHL PERFORMANCE New leads this month ¦ Automation performance ¦ Reviews generated ¦ Missed calls recovered SECTION 5 — WHAT WE OPTIMIZED 3–5 specific actions taken this month and the reason for each SECTION 6 — NEXT MONTH PLAN 3 specific actions we will take. This shows proactivity and accountability.

🛡️  CLIENT RETENTION — RED FLAGS & RESPONSE PROTOCOL

| Red Flag | Response Action | Owner | Resolved? |
| --- | --- | --- | --- |
| Client goes 7+ days without responding to any communication | AM escalates to Senior AM — proactive outreach call scheduled immediately | Senior AM | ☐ |
| Lead volume drops 30%+ week-over-week with no clear explanation | Ad Specialist investigates same day — AM notifies client proactively before they notice | Ad Specialist + AM | ☐ |
| Client mentions a competitor or asks about cancellation | AM escalates to Senior AM within 1 hour — retention call scheduled within 24 hours | Senior AM | ☐ |
| Client misses 2+ scheduled calls in a row | Flag as churn risk in GHL — tag 'At Risk' — Senior AM outreach | Senior AM | ☐ |
| Monthly payment fails | GHL billing alert fires — AM contacts client within 2 hours — resolve same day | AM | ☐ |
| Client leaves a negative review about the agency | Director responds publicly within 4 hours — private outreach same day | Director | ☐ |

⬆️  UPSELL & EXPANSION TRIGGERS

The best time to grow a client's package is when they're seeing results. These triggers indicate a client is ready for the upsell conversation.

UPSELL TRIGGERS — BRING TO QUARTERLY REVIEW Ads Only Client (no social): Trigger when CPL is strong for 60+ days → pitch social media add-on Social Only Client (no ads): Trigger when follower growth is plateauing → pitch Google Ads to drive traffic Google Only (no Meta): Trigger when Google budget is maxed and CPL is stable → pitch Meta for additional volume No LSA: Trigger when Google Search CPL is above $80 → LSA often delivers cheaper leads for same service Low review count (<20 Google reviews): Trigger when jobs are being completed → automate review requests via GHL Poor website conversion: Trigger when CTR is strong but form fills are low → pitch landing page or CRO service High call volume but low close rate: Trigger when call recordings show missed opportunities → pitch sales training

🔶 GO HIGH LEVEL: CONTACT RECORD → Custom Fields → Update 'Services Active', 'Upsell Opportunity', 'Next Upsell Target' → Create task for AM: 'Present [upsell] at next quarterly review' → Track upsell pipeline in Agency Sales Pipeline

| 9 | ESCALATION PATH & COMMUNICATION STANDARDS How we handle problems and keep clients informed |
| --- | --- |

📣  ESCALATION PATH

| Issue Occurs → | Ad Specialist → | Account Manager → | Senior AM → | Director |
| --- | --- | --- | --- | --- |

- Ad Specialist handles: tracking issues, campaign anomalies, disapprovals, creative performance

- Account Manager handles: client communication, missed reports, mild dissatisfaction, minor complaints

- Senior AM handles: cancellation threats, billing disputes, major performance failures, client escalations

- Director handles: legal issues, public complaints, client threatening reviews, extreme dissatisfaction

💬  COMMUNICATION STANDARDS — NON-NEGOTIABLE

| RESPONSE TIME STANDARDS • Client email/message: reply within 4 business hours • Client call: return within 2 hours during business hours • Urgent issue (account suspended, tracking broken): respond within 1 hour • Bad news to deliver: proactively — never let client discover first • New lead notification to client: immediate (via GHL automation) • Monthly report: delivered by 5th of each month — no exceptions | ALL CLIENT COMMUNICATION LOGGED IN GHL • Every call: logged in GHL contact record within 2 hours with summary notes • Every email: sent from or BCC'd to GHL for conversation tracking • Every meeting: logged with agenda and outcome in GHL notes • Every optimization: documented in GHL client notes with date and reason • Every client complaint: tagged in GHL + escalated per protocol |
| --- | --- |

🔶 GO HIGH LEVEL: CONVERSATIONS → Use GHL as the primary client communication hub → All SMS, email, and call logs stored here → AM reviews their client conversations every Monday morning

🏆 THE GOLDEN STANDARD — WHAT GREAT LOOKS LIKE A client who has been with us 6+ months should: ✓ Receive their monthly report by the 5th — every single month ✓ Have every call and form lead appear in their GHL inbox within 60 seconds of submission ✓ Have all leads followed up with automatically within 5 minutes via SMS ✓ See new Google reviews coming in every month from our post-job automation ✓ Have a content specialist at their site once a month keeping their social media active ✓ Never have to call us asking 'how are my campaigns doing?' — we tell them first ✓ Feel like we are an extension of their team, not a vendor they have to manage This is not the minimum. This is the standard. Every client. Every month.

Questions? Contact your Senior Account Manager or Director of Operations  |  Complete Client Journey Guide — San Diego Contractor Marketing 2025